Software Reengineering

Estimation Techniques for AuralAid

FPC, UCP and COCOMO Model

Submitted To:
Mr. Junaid Ali Khan

Project Title:
AuralAid: Adaptive AI Hearing with Contextual Understanding

| Prepared For | Department of Software Engineering, HITEC University, Taxila |
| --- | --- |
| Based On Proposal | AuralAid Project Proposal |

# Function Point Calculation

Functional components are categorized and weighted based on complexity in order to estimate the size of AuralAid. The estimation below is aligned to the technical scope of the project proposal, including real-time audio capture, noise filtering, speech-to-text captioning, emotion detection, health monitoring, safety alerts, and mobile app connectivity.

| Function | Type | Complexity | Weight | Function Points |
| --- | --- | --- | --- | --- |
| User registration / profile setup | EI | Low | 3 | 3 |
| Device pairing and configuration | EI | Medium | 4 | 4 |
| Live audio stream capture | EI | High | 6 | 6 |
| Health sensor data intake (HR, SpO₂, temperature) | EI | High | 6 | 6 |
| Caption generation request / session start | EI | Medium | 4 | 4 |
| Noise-alert threshold configuration | EI | Low | 3 | 3 |
| Live speech-to-text captions | EO | High | 7 | 7 |
| Emotion detection feedback | EO | High | 7 | 7 |
| Noise hazard alerts | EO | Medium | 5 | 5 |
| Health anomaly alerts | EO | High | 7 | 7 |
| Session summaries / logs | EO | Medium | 5 | 5 |
| User profiles and preferences | ILF | Medium | 10 | 10 |
| Caption and conversation history | ILF | Medium | 10 | 10 |
| Health monitoring records | ILF | Medium | 10 | 10 |
| Device/session logs | ILF | Low | 7 | 7 |
| External speech recognition service / model | EIF | Medium | 7 | 7 |
| backup / notification service | EIF | Low | 5 | 5 |
| Query caption history | EQ | Medium | 4 | 4 |
| Query health trends / alerts | EQ | Medium | 4 | 4 |
| Query session and noise-event reports | EQ | Medium | 4 | 4 |
|  |  |  |  | 118 |

## Environment Adjustment Factor / Value Adjustment Factor

The complexity of AuralAid is influenced by its hybrid embedded, AI, mobile, and health-monitoring workflow. The following ratings adapt the same estimation structure used in the reference document, but the values are customized for AuralAid.

| Factor | Rating | Explanation |
| --- | --- | --- |
| Data Communication | 4 | Continuous BLE/Wi-Fi exchange between wearable hardware and mobile application. |
| Distributed Data Processing | 3 | Edge processing on ESP32-S3 with optional mobile/cloud support. |
| Performance | 4 | Low-latency captioning, alerting, and audio-response workflow. |
| Heavily Used Configuration | 3 | Frequent caption, audio, and alert sessions under daily use. |
| Transaction Rate | 3 | Moderate to high event rate for captions, sensor samples, and alerts. |
| Online Data Entry | 3 | User settings, thresholds, profile values, and app interactions are entered live. |
| End-User Efficiency | 4 | Assistive workflow requires clear and immediate interaction. |
| Complex Processing | 4 | DSP, speech recognition, emotion analysis, and anomaly detection increase complexity. |
| Reusable Code | 2 | Some reusable libraries and SDK support are available. |
| Installation Ease | 2 | Prototype setup is manageable but hardware pairing adds effort. |
| Operational Ease | 3 | Device maintenance, sensor calibration, and app support are required. |
| Multiple Sites | 2 | Solution can be used by users in different environments and contexts. |
| Facilitate Change | 3 | AI models, thresholds, and app features may evolve during development. |
| Concurrency | 3 | System must manage simultaneous audio, sensor, and UI events. |

Total Sum of Ratings = 43

Non-standard EAF style ratio = 43 / 14 ≈ 3.07

Standard IFPUG VAF = 0.65 + (43 × 0.01) = 1.08

Adjusted Function Points = 118 × 1.08 ≈ 127

## Interpretation

The standard VAF-based adjusted function point count is preferred for the final estimate because it is more conservative and consistent with industry-style function point adjustment. The environmental ratio is still shown because AuralAid has substantial real-time, embedded, and AI-related complexity.

# Use Case Point Calculation

Each use case is categorized as Simple (5), Average (10), or Complex (15) based on the amount of interaction, decision logic, and technical coordination needed across embedded, AI, and app modules.

| Use Case | Transactions | Complexity | Weight |
| --- | --- | --- | --- |
| UC-001: User Registration / Login | 5 | Average | 10 |
| UC-002: Device Pairing & App Connectivity | 6 | Average | 10 |
| UC-003: Capture & Filter Audio | 7 | Complex | 15 |
| UC-004: Real-Time Speech to Text | 7 | Complex | 15 |
| UC-005: Emotion Detection | 6 | Average | 10 |
| UC-006: Noise Alert Handling | 5 | Average | 10 |
| UC-007: Health Monitoring | 7 | Complex | 15 |
| UC-008: Send Health / Safety Alerts | 5 | Average | 10 |
| UC-009: View Caption / Health History | 4 | Average | 10 |

Unadjusted Use Case Weight (UUCW) = 105

## Evaluate Actors

| Actor | Type | Weight |
| --- | --- | --- |
| User / Patient | Complex | 3 |
| Healthcare Provider / Admin | Average | 2 |
| Mobile App | Complex | 3 |
| Speech Recognition Service | Simple | 1 |
| Emotion Detection Service / Model | Simple | 1 |
| backup/ Notification Service | Simple | 1 |
| Wearable Sensor Subsystem | Average | 2 |
| BLE / Wi-Fi Communication Layer | Average | 2 |

Unadjusted Actor Weight (UAW) = 15

Unadjusted Use Case Points (UUCP) = UUCW + UAW = 105 + 15 = 120

## Adjust for Technical and Environmental Factors

Technical Complexity Factor (TCF) = 0.6 + (0.01 × 44) = 1.04

Environmental Factor (EF) = 1.4 + (−0.03 × 20) = 0.80

Adjusted Use Case Points (UCP) = 120 × 1.04 × 0.80 ≈ 99.8

## Estimated Effort from UCP

Assuming 20–30 person-hours per UCP:

Low estimate = 99.8 × 20 ≈ 1,997 hours

High estimate = 99.8 × 30 ≈ 2,995 hours

Average effort ≈ 2,496 person-hours

## Final UCP Result

Unadjusted Use Case Points (UUCP): 120

Adjusted Use Case Points (UCP): ~99.8

Estimated Effort: 1,997–2,995 hours (median ~2,496 hours)

# Converting Function Points to Lines of Code (LOC)

COCOMO uses LOC/KLOC for effort estimation. Since AuralAid spans embedded C/C++, Flutter/Dart, and AI-support code, a mixed-language conversion rate is assumed.

LOC per FP = 55

Total LOC = 127 FP × 55 LOC/FP = 6,985 LOC (7.0 KLOC)

# Basic COCOMO Estimation

Project Type: Semi-Detached. This classification is suitable because AuralAid combines embedded firmware, AI-enabled processing, mobile integration, and moderate multidisciplinary coordination.

Formulas:

Effort = a × (KLOC)^b

Schedule = 2.5 × (Effort)^c

Coefficients used for Semi-Detached: a = 3.0, b = 1.12, c = 0.35

Effort = 3.0 × (7.0)^1.12 ≈ 17.4 Person-Months

Schedule = 2.5 × (17.4)^0.35 ≈ 6.8 Months

Cost at $5,000 per person-month ≈ $86,912

# Intermediate COCOMO Estimation

| Cost Driver | Rating | Effort Multiplier |
| --- | --- | --- |
| Required Reliability (RELY) | High | 1.15 |
| Product Complexity (CPLX) | Very High | 1.30 |
| Execution Time Constraint (TIME) | High | 1.11 |
| Analyst Capability (ACAP) | Nominal | 1.00 |
| Programmer Capability (PCAP) | High | 0.86 |
| Applications Experience (AEXP) | Nominal | 1.00 |
| Tool Usage (TOOL) | Nominal | 1.00 |
| Schedule Pressure (SCED) | High | 1.12 |

Effort Adjustment Factor (EAF) = 1.15 × 1.30 × 1.11 × 1.00 × 0.86 × 1.00 × 1.00 × 1.12 ≈ 1.60

Adjusted Effort = 17.4 × 1.60 ≈ 27.8 Person-Months

Estimated Schedule ≈ 8.0 Months

Estimated Cost ≈ $138,919

# Summary of Estimates

| Model | Effort | Schedule | Cost |
| --- | --- | --- | --- |
| Basic COCOMO | 17.4 Person-Months | 6.8 Months | $86,912 |
| Intermediate COCOMO | 27.8 Person-Months | 8.0 Months | $138,919 |

# Key Assumptions & Notes

Function point and use case values are adapted to the AuralAid proposal rather than copied from the SkillBoost example.

The estimate includes real-time audio handling, speech-to-text, emotion analysis, health monitoring, mobile connectivity, alerting, and data history features.

LOC/FP = 55 is assumed for the mixed embedded/mobile/AI codebase. This should be recalibrated if the final implementation shifts more heavily toward external APIs or prebuilt frameworks.

COCOMO is only an estimation model. AI-assisted features, pre-trained models, and hardware integration often require iterative validation that is not perfectly captured by classical software-only sizing.

$5,000 per person-month is used only as a placeholder labor rate and should be adjusted for the actual region and staffing structure.

# Recommendations

Use the adjusted function point and UCP results as planning baselines for scope and team effort discussions.

Use Intermediate COCOMO for budgeting because it better reflects AuralAid’s reliability, complexity, and schedule pressure.

Re-estimate after the architecture is finalized, especially when the team decides which processing is on-device, mobile-side, or cloud-assisted.

Reserve additional effort for hardware debugging, sensor calibration, real-world noise testing, model tuning, and user validation with assistive workflows.