## Lessons Learned Template
Lessons Learned Report
Today's Date: | 2026-01-24
Project Name: | AuralAid: Adaptive AI Hearing with Contextual Understanding
Project Manager: | Ayesha Nazir
Notes: | The project is in development phase with hardware integration, AI model testing, and mobile app development underway.
WIN or ISSUE | Describe What Happened | What Was the Impact? | How Does This Change Future Projects? | Action Items
WIN | Successfully integrated MEMS microphones with ESP32-S3 for real-time audio capture and DSP processing. | Improved audio clarity and reliable real-time sound processing. | Future projects will follow modular embedded system integration. | 1. Document hardware integration steps 2. Create reusable DSP modules
ISSUE | Initial difficulty in AI model deployment on low-resource devices. | Delay in emotion detection and speech model integration. | Future projects will include early AI feasibility testing. | 1. Prototype AI models early 2. Use lightweight models
WIN | Effective team collaboration using GitHub for code and documentation. | Smooth development flow and reduced merge conflicts. | Version control will remain mandatory for all projects. | 1. GitHub best practices guide 2. Team training sessions
ISSUE | Bluetooth connectivity instability during early testing. | Data transmission delays between device and app. | Future designs will include early communication testing. | 1. BLE stress testing 2. Backup communication protocols
WIN | Successful development of Flutter mobile app interface. | User-friendly real-time caption and alert display. | UI/UX design will be prioritized early. | 1. UI component library 2. Design documentation
WIN | Noise alert and vibration system integrated successfully. | Improved user safety awareness. | Safety systems will be core features. | 1. Standard safety module 2. Alert testing framework
WIN | Modular system architecture implementation. | Scalable design and faster development. | Modular architecture will be standard practice. | 1. Modular design documentation 2. Training for juniors

## How to Use This Template
How to Use Our Lessons Learned Template
The lessons learned template is a tool to note what worked and what didn't in your project to repeat the positive and avoid the negative.
Today's Date: Enter today’s date
Project Name: Give your project a name, so it can be quickly identified
Project Manager: Enter the name of the person overseeing the project. This could be a proper project manager or any staff member who is the owner of the work.
Notes: This field is for you to add any relevant information you’d like. Ideas: client name, stakeholders, project summary, budget, etc.
WIN or ISSUE: Choose either WIN or ISSUE to classify the lesson. A win is something positive that happened, and an issue is something negative that happened
Describe What Happened: Use this field to give a detailed description of the lesson you learned
What Was the Impact?: Here, you’ll describe the positive or negative result, and the impact there may have been. For a win, write about the positive outcome that occurred. For an issue, write about the negative consequences you experienced due to the problem
How Does This Change Future Projects?: In this field, record your thoughts on how this lesson might impact future work. Think about how other people in your organization might benefit from learning this lesson
Action Items: Add the actionable steps that will be taken to address your win or issue. Every row should have an action item, even if it is as simple as “monitor to see if it happens again.” This is the most important part of the template, because you are outlining the steps you will take to improve