## Task_Table1
Name | WBS | Number of Dots | Substitute last dot | Location hash | get left text | Match | Parent
SkillBoost ¦ Your AI Powered Path to Success | 1 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Project Initiation | 2 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Requirement Gathering | 2.1 | 1 | 2#1 | 2 | 2 | 2 | Project Initiation
Identify Stakeholders | 2.1.1 | 2 | 2.1#1 | 4 | 2.1 | 3 | Requirement Gathering
Gather Requirements | 2.1.2 | 2 | 2.1#2 | 4 | 2.1 | 3 | Requirement Gathering
Analyze Market Needs | 2.1.3 | 2 | 2.1#3 | 4 | 2.1 | 3 | Requirement Gathering
Document Creation | 2.2 | 1 | 2#2 | 2 | 2 | 2 | Project Initiation
Prepare Business Case | 2.2.1 | 2 | 2.2#1 | 4 | 2.2 | 7 | Document Creation
Draft Statement of Work | 2.2.2 | 2 | 2.2#2 | 4 | 2.2 | 7 | Document Creation
Develop Project Charter | 2.2.3 | 2 | 2.2#3 | 4 | 2.2 | 7 | Document Creation
Planning Phase | 3 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Define Project Scope | 3.1 | 1 | 3#1 | 2 | 3 | 11 | Planning Phase
Identify Deliverables | 3.1.1 | 2 | 3.1#1 | 4 | 3.1 | 12 | Define Project Scope
Identify Requirements | 3.1.2 | 2 | 3.1#2 | 4 | 3.1 | 12 | Define Project Scope
Develop Project Plan | 3.2 | 1 | 3#2 | 2 | 3 | 11 | Planning Phase
Define Project Timeline | 3.2.1 | 2 | 3.2#1 | 4 | 3.2 | 15 | Develop Project Plan
Identify Resources | 3.2.2 | 2 | 3.2#2 | 4 | 3.2 | 15 | Develop Project Plan
Risk Management Planning | 3.3 | 1 | 3#3 | 2 | 3 | 11 | Planning Phase
Identify Risks | 3.3.1 | 2 | 3.3#1 | 4 | 3.3 | 18 | Risk Management Planning
Analyze Risks | 3.3.2 | 2 | 3.3#2 | 4 | 3.3 | 18 | Risk Management Planning
Develop Mitigation Strategies | 3.3.3 | 2 | 3.3#3 | 4 | 3.3 | 18 | Risk Management Planning
Develop Resource Management Plan | 3.4 | 1 | 3#4 | 2 | 3 | 11 | Planning Phase
Identify Resource Needs | 3.4.1 | 2 | 3.4#1 | 4 | 3.4 | 22 | Develop Resource Management Plan
Allocate Resources | 3.4.2 | 2 | 3.4#2 | 4 | 3.4 | 22 | Develop Resource Management Plan
Design And Developemnt | 4 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Interface Design | 4.1 | 1 | 4#1 | 2 | 4 | 25 | Design And Developemnt
Develop Wireframes | 4.1.1 | 2 | 4.1#1 | 4 | 4.1 | 26 | Interface Design
Design Homepage | 4.1.1.1 | 3 | 4.1.1#1 | 6 | 4.1.1 | 27 | Develop Wireframes
Design Feature Interface | 4.1.1.2 | 3 | 4.1.1#2 | 6 | 4.1.1 | 27 | Develop Wireframes
Design Simukation Interface | 4.1.1.3 | 3 | 4.1.1#3 | 6 | 4.1.1 | 27 | Develop Wireframes
User Interaction Testing | 4.1.2 | 2 | 4.1#2 | 4 | 4.1 | 26 | Interface Design
Prepare Testing Plan | 4.1.2.1 | 3 | 4.1.2#1 | 6 | 4.1.2 | 31 | User Interaction Testing
Conduct Usability Tests | 4.1.2.2 | 3 | 4.1.2#2 | 6 | 4.1.2 | 31 | User Interaction Testing
Analyze User Feedback | 4.1.2.3 | 3 | 4.1.2#3 | 6 | 4.1.2 | 31 | User Interaction Testing
Technical Infrastructure | 4.2 | 1 | 4#2 | 2 | 4 | 25 | Design And Developemnt
Backend Development | 4.2.1 | 2 | 4.2#1 | 4 | 4.2 | 35 | Technical Infrastructure
Implement Authentication | 4.2.1.1 | 3 | 4.2.1#1 | 6 | 4.2.1 | 36 | Backend Development
Frontend Development | 4.2.2 | 2 | 4.2#2 | 4 | 4.2 | 35 | Technical Infrastructure
Design React Components | 4.2.2.1 | 3 | 4.2.2#1 | 6 | 4.2.2 | 38 | Frontend Development
Create Responsive Layout | 4.2.2.2 | 3 | 4.2.2#2 | 6 | 4.2.2 | 38 | Frontend Development
Simulation Features | 4.3 | 1 | 4#3 | 2 | 4 | 25 | Design And Developemnt
AI-Powered Interview Simulation | 4.3.1 | 2 | 4.3#1 | 4 | 4.3 | 41 | Simulation Features
Create Question Modules | 4.3.1.1 | 3 | 4.3.1#1 | 6 | 4.3.1 | 42 | AI-Powered Interview Simulation
Categorize Questions | 4.3.1.1.1 | 4 | 4.3.1.1#1 | 8 | 4.3.1.1 | 43 | Create Question Modules
Define Scoring Criteria | 4.3.1.1.2 | 4 | 4.3.1.1#2 | 8 | 4.3.1.1 | 43 | Create Question Modules
Real-Time Feedback Mechanism | 4.3.2 | 2 | 4.3#2 | 4 | 4.3 | 41 | Simulation Features
Develop Feedback Format | 4.3.2.1 | 3 | 4.3.2#1 | 6 | 4.3.2 | 46 | Real-Time Feedback Mechanism
Test Feedback Algorithms | 4.3.2.2 | 3 | 4.3.2#2 | 6 | 4.3.2 | 46 | Real-Time Feedback Mechanism
Code Optimizer | 4.4 | 1 | 4#4 | 2 | 4 | 25 | Design And Developemnt
Implement functionality to calculate time complexity | 4.4.1 | 2 | 4.4#1 | 4 | 4.4 | 49 | Code Optimizer
Implement functionality to calculate space complexity | 4.4.2 | 2 | 4.4#2 | 4 | 4.4 | 49 | Code Optimizer
Develop logic for identifying inefficiencies | 4.4.3 | 2 | 4.4#3 | 4 | 4.4 | 49 | Code Optimizer
Resume Analyzer | 4.5 | 1 | 4#5 | 2 | 4 | 25 | Design And Developemnt
AI-Powered CV Evaluation | 4.5.1 | 2 | 4.5#1 | 4 | 4.5 | 53 | Resume Analyzer
Set Analysis Parameters | 4.5.1.1 | 3 | 4.5.1#1 | 6 | 4.5.1 | 54 | AI-Powered CV Evaluation
Title-Based Filtering | 4.5.1.1.1 | 4 | 4.5.1.1#1 | 8 | 4.5.1.1 | 55 | Set Analysis Parameters
Keyword Based Filtering | 4.5.1.1.2 | 4 | 4.5.1.1#2 | 8 | 4.5.1.1 | 55 | Set Analysis Parameters
Generate Feedback Reports | 4.5.2 | 2 | 4.5#2 | 4 | 4.5 | 53 | Resume Analyzer
Improvement Suggestions | 4.5.2.1 | 3 | 4.5.2#1 | 6 | 4.5.2 | 58 | Generate Feedback Reports
Integrate Results Dashboard | 4.5.3 | 2 | 4.5#3 | 4 | 4.5 | 53 | Resume Analyzer
Save and Display Results | 4.5.3.1 | 3 | 4.5.3#1 | 6 | 4.5.3 | 60 | Integrate Results Dashboard
AI Model Training | 5 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Data Collection | 5.1 | 1 | 5#1 | 2 | 5 | 62 | AI Model Training
Candidate Profile Collection | 5.1.1 | 2 | 5.1#1 | 4 | 5.1 | 63 | Data Collection
Research and Identify Data Sources | 5.1.1.1 | 3 | 5.1.1#1 | 6 | 5.1.1 | 64 | Candidate Profile Collection
Gather sample resumes and profiles for training. | 5.1.1.2 | 3 | 5.1.1#2 | 6 | 5.1.1 | 64 | Candidate Profile Collection
Preprocess and clean collected data. | 5.1.1.3 | 3 | 5.1.1#3 | 6 | 5.1.1 | 64 | Candidate Profile Collection
Industry Analysis Data | 5.1.2 | 2 | 5.1#2 | 4 | 5.1 | 63 | Data Collection
Collect industry trends and job market data. | 5.1.2.1 | 3 | 5.1.2#1 | 6 | 5.1.2 | 68 | Industry Analysis Data
Aggregate required skills for various job roles | 5.1.2.2 | 3 | 5.1.2#2 | 6 | 5.1.2 | 68 | Industry Analysis Data
Validate and standardize data for use. | 5.1.2.3 | 3 | 5.1.2#3 | 6 | 5.1.2 | 68 | Industry Analysis Data
Model Development | 5.2 | 1 | 5#2 | 2 | 5 | 62 | AI Model Training
Model Architecture Design | 5.2.1 | 2 | 5.2#1 | 4 | 5.2 | 72 | Model Development
Define architecture suitable for resume parsing and optimization | 5.2.1.1 | 3 | 5.2.1#1 | 6 | 5.2.1 | 73 | Model Architecture Design
Create initial architecture diagrams | 5.2.1.2 | 3 | 5.2.1#2 | 6 | 5.2.1 | 73 | Model Architecture Design
Algorithm Training | 5.3 | 1 | 5#3 | 2 | 5 | 62 | AI Model Training
Develop training datasets with labeled data. | 5.3.1 | 2 | 5.3#1 | 4 | 5.3 | 76 | Algorithm Training
identify optimization techniques to improve accuracy | 5.3.2 | 2 | 5.3#2 | 4 | 5.3 | 76 | Algorithm Training
Evaluation and Tuning | 5.4 | 1 | 5#4 | 2 | 5 | 62 | AI Model Training
Test the model on unseen data | 5.4.1 | 2 | 5.4#1 | 4 | 5.4 | 79 | Evaluation and Tuning
Tune hyperparameters | 5.4.2 | 2 | 5.4#2 | 4 | 5.4 | 79 | Evaluation and Tuning
Create performance evaluation metrics | 5.4.3 | 2 | 5.4#3 | 4 | 5.4 | 79 | Evaluation and Tuning
Testing and Quality Assurance | 6 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Module Testing | 6.1 | 1 | 6#1 | 2 | 6 | 83 | Testing and Quality Assurance
Interview Simulation Testing | 6.1.1 | 2 | 6.1#1 | 4 | 6.1 | 84 | Module Testing
Code Assessment Testing | 6.1.2 | 2 | 6.1#2 | 4 | 6.1 | 84 | Module Testing
CV Evaluation Testing | 6.1.3 | 2 | 6.1#3 | 4 | 6.1 | 84 | Module Testing
System Integration Testing | 6.2 | 1 | 6#2 | 2 | 6 | 83 | Testing and Quality Assurance
Backend-Frontend Sync | 6.2.1 | 2 | 6.2#1 | 4 | 6.2 | 88 | System Integration Testing
AI Model Integration | 6.2.2 | 2 | 6.2#2 | 4 | 6.2 | 88 | System Integration Testing
User Acceptance Testing | 6.3 | 1 | 6#3 | 2 | 6 | 83 | Testing and Quality Assurance
Beta User Feedback | 6.3.1 | 2 | 6.3#1 | 4 | 6.3 | 91 | User Acceptance Testing
Iterative Improvements Based on Feedback | 6.3.2 | 2 | 6.3#2 | 4 | 6.3 | 91 | User Acceptance Testing
Deployment | 7 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Setup Hosting | 7.1 | 1 | 7#1 | 2 | 7 | 94 | Deployment
Cloud Service Configuration | 7.1.1 | 2 | 7.1#1 | 4 | 7.1 | 95 | Setup Hosting
Security Protocols | 7.1.2 | 2 | 7.1#2 | 4 | 7.1 | 95 | Setup Hosting
Final Review and Approval | 7.2 | 1 | 7#2 | 2 | 7 | 94 | Deployment
Project Approval | 7.2.1 | 2 | 7.2#1 | 4 | 7.2 | 98 | Final Review and Approval
Deployment Checklist | 7.2.2 | 2 | 7.2#2 | 4 | 7.2 | 98 | Final Review and Approval
Launch | 7.3 | 1 | 7#3 | 2 | 7 | 94 | Deployment
Marketing Campaigns | 7.3.1 | 2 | 7.3#1 | 4 | 7.3 | 101 | Launch
Platform Launch Event | 7.3.2 | 2 | 7.3#2 | 4 | 7.3 | 101 | Launch
Maintenance and Updates | 8 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
User Support | 8.1 | 1 | 8#1 | 2 | 8 | 104 | Maintenance and Updates
FAQ and Support Resources | 8.1.1 | 2 | 8.1#1 | 4 | 8.1 | 105 | User Support
Continuous User Feedback collection | 8.1.2 | 2 | 8.1#2 | 4 | 8.1 | 105 | User Support
Platform Enhancements | 8.2 | 1 | 8#2 | 2 | 8 | 104 | Maintenance and Updates
Feature Updates | 8.2.1 | 2 | 8.2#1 | 4 | 8.2 | 108 | Platform Enhancements
AI Model Optimization | 8.2.2 | 2 | 8.2#2 | 4 | 8.2 | 108 | Platform Enhancements
Bug Fixes and Issue Resolution | 8.3 | 1 | 8#3 | 2 | 8 | 104 | Maintenance and Updates
Regular Issue Tracking | 8.3.1 | 2 |  | #VALUE! | #VALUE! | #VALUE!